## Summary
LCC Parks 4090000 - NA Review Programme - Status Summary
Prepared 11-Jun-2026; updated 16-Jun-2026 ¦ Spero Karkalemis ¦ Ledger 26SLACT, O110-O115, P1-12 ¦ No emails per standing directive; decisions are Spero's
IN-SCOPE SPEND (87 ACCOUNTS) | REVIEWED $ (SE2 COVERAGE BASIS) | REVIEWED % OF SPEND | ACCOUNTS WITH A REGISTER ROW
33891610.16 | 497902.68 | 1.469% | 21 of 87
FULLY REVIEWED | PARTIAL | OPENED (NOT RECONCILED) | NOT STARTED
13 | 7 | 1 | 66
Overall RAG across register accounts ¦ GREEN clear, AMBER confirm, RED blocker, OPENED pre-reconciliation
GREEN | AMBER | RED | OPENED
2 | 18 | 0 | 1
Session headlines, 11-Jun-2026
- Derived workbooks extended 11-Jun-2026 (fourth pass): the five handover workstreams (73211, 62121/62125, 7B532, 7B214, 73541) now carry rows here, in the Tracker and in the Running Transaction Listing (133 new listing lines).
- 73211 worked and evidenced: intake C00228240 applied, 43 documents sighted, $157,051.42 of $236,378.27 (66.4%), all exact on the x1.1 test, 18 ABNs PASS; F5/F6 closed, F7 raised; GSTE-28 Telstra pattern recorded.
- 73211 candidates held un-instructed (no recode dollar populated): F1 GJ079190 reversal, F2 ~$98,005 to 73212, F3 training/chair items, six new classification candidates.
- 7B532 probable $1,232 IJ072723 duplicate held AMBER; 7B214 $7,488 oncharge backups outstanding; 62121/62125 destination-leg confirmation is the Garside residue; 73541 closes on the Trailbuilders backup.
- Hard gates NONE. Register 22 rows, $538,947.73 ex-GST reviewed (recalc-verified); 16-Jun intake added NA7B213 Internal Medical (Immunisation) $4,861.70 and refreshed 73211 to $267,532.19 (+6 P12 lines, +$31,153.92, 17-Jun re-export); 73123 remains OPENED, not reconciled (gap $50,338.64).
Basis note: SE2-coverage Reviewed-$ is anchored to the fixed 8-Jun SE2 and bridges to the register total $538,947.73 below. Differences: 73511 ($1,117.08, FBT batch pairs), 73512 ($8.42), post-SE2 P12 postings on 73211 ($31,454.92, incl the 17-Jun re-export's 6 new lines) and 7B214 ($3,888.00), the new 7B213 immunisation export over SE2 ($864.90), and the 62121/62125 revenue supplementary ($3,711.73) outside the 87-account expense scope. The tie-out below recomputes the bridge live.
Register tie-out (live): SE2-coverage Reviewed-$ bridged to the Account Review Register
Reviewed $ (SE2-coverage basis, 87 accounts) | 497902.68
+ 73511 basis difference (register $5,384.57 net of FBT batch pairs) | 1117.08
+ 73512 basis difference (register $5,520.97 post-SE2) | 8.42
+ 73211 basis difference (register $267,532.19; +6 P12 lines, 17-Jun re-export) | 31454.92
+ 7B214 basis difference (register $7,570.50; P12 IJ074845) | 3888
+ 7B213 basis difference (register $4,861.70; post-SE2 immunisation export) | 864.9
+ 62121/62125 supplementary (revenue, outside the 87) | 3711.73
Register reviewed total (computed, = sum of the seven rows above) | 538947.73
Register total per 00_Account_Review_Register.xlsx, 22 rows, 16-Jun-2026 | 538947.73
Tie-out | TIES

## All Accounts
LCC Parks 4090000 - Natural Account Review - Status of All Accounts
All 87 in-scope natural accounts ¦ Source SE2 8-Jun-2026, register and tracker as at 11-Jun-2026 ¦ Batch CN-23167 ¦ GL ex-GST
Priority | NA | Account name | Accum actual ex-GST | Annual budget | Materiality | Review status | Reviewed $ | Untested $ | L1 PK | L2 NA | L3 Evid | L4 Tax | Overall RAG | Key finding (condensed) | Remaining items | Evidence / artefacts | Journal status | Last reviewed
P1 | 72111 | Minor Equipment & Supplies | 67055.47 | 97083.52 | $10k-100k | Partial | 3433.91 | 63621.56 | GREEN | RED | GREEN | GREEN | AMBER | AP-invoice pass: $2,260.36 of $3,433.91 miscoded (Tennyson signage 72222, Ultimate PPE 72113, STIHL GTA 40 72315, INITIATOR chem 72112). Doc46 journal pass recodes $22,028 off 72111 across 11 NAs. The two OVERLAP (Tennyson 27577 $335 in both) and cannot be summed. EVIDENCE SIGHTED 9-Jun (Ultimate/Woodmans/Tennyson set C00267478, all ABNs PASS): 3 Trees-PK (20241/PK000055) recodes now STAGED in NA72111_GENJNL_Recode.txt - trousers PIK2270125 $292.09 and pants PIK2267644 $402.59 to 72113 PPE (part... | 1 Upload the 72111 streams (in the live journal). 2 Process GSTE-01 to 03 BAS adjustments ($69.50). 3 Spero scope call on the $63,621.56 untested remainder. Oasis/Pac Fire/Bunnings receipt GAPs closed 10-Jun-2026 (all four sighted, ABNs PASS, reconcile to the cent); Doc46 partial-recode remainders now content-known (PPE/decor candidates, un-instructed). | NA72111 note; _CarryForward Doc46/Doc45 source journals | CN-23167 (PREPARED; NA72111_GENJNL_Recode.txt 14 lines, 4 sets) | 9-Jun-2026
P1 | 73564 | IT Equipment and Applications | 43393.37 | 60215.21 | $10k-100k | Fully reviewed | 43393.37 | 0 | AMBER | AMBER | AMBER | AMBER | AMBER | Full account $43,393.37 ex-GST, 36 lines (was partial $1,929.27). Findings: (a) 6 software/subscription lines $1,822.45 belong in 73566 IT Software Licence Fees (Esri, Anthropic, Body2 x2, 2 licence bundles); chart + P10 Canva/VisitUs precedent. (b) 9 of 20 recharge lines $4,416.27 off officer home PK incl confirmed Fry Depots->Trees miscode and likely AnneMarie/Caroline King mixup. (c) Esri INV000555 tax COMPLIANT (ABN PASS, GST exact, 1 of 7 seats). Body2 L18/L19 = correct monthly recognition ... | 1 Finance accept 73564->73566 software recode $1,822.45 (held); confirm Body2 moved or left. 2 Confirm IT-recharge PK convention (home vs supported-team) for 9 lines. 3 Fry attribution CONFIRMED PK000001 (analyst); both positions map to PK000001. Release net-move 20241/PK000055->20151/PK000001 on SR-0315517 sighting. 4 Resolve King L08/L24 svc20191/PK000082. 5 Sight 7 no-attach SR backups: SR-0316577, SR-0315241, SR#204868, SR-0312575, SR#201404, SR-0315517, SR#200930 ($6,689.87). 6 Sight + tax-check 5 external invoices: 2412569490, INAU004378, GJ076194, GJ075813, TE005499. 6 Query L34 $3,761.60 quantum. 7 Advisory: P&A register for iPad/iPhone fleet. UPDATE 9-Jun: PK convention = officer home PK (Spero); 3 net-moves staged (Robertson/Dressman/Fry); sight SR219175/SR235810/SR-0315517 to clear their evidence limb; 6 King/Shearman lines still pending. | NA73564_Evidence/ (Esri INV000555 sighted; ledger extract); NA73564_GENJNL_Recode.txt (held; IT recharge schedule Feb-2026 sighted 10-Jun) | CN-23167 (journal-ready, Spero; A 73564->73566 software, B 3 PK net-moves) | 9-Jun-2026
P1 | 72312 | Office & Library Equipment | 2461.27 | 0 | $1k-10k | Fully reviewed | 2461.27 |  | GREEN | RED | GREEN | GREEN | AMBER | $2,461.27 of $2,461.27 (100%) miscoded out of 72312; IKEA EKET cabinets and Empire chair gas lifts + desk power + install all belong in 72313 Furniture & Fittings. IKEA line PK000493 CONFIRMED valid (Flying Gang, Park Services, svc 20392) per analyst sub-PK ledger; PK preserved as transacted, no PK move. Both ABNs checksum PASS. | 1 Finance accept 72312 to 72313 recode in full-reversal format, then release CN-23167. 2 CAVEAT: pk_validator fails PK000493 (absent from installed maps which carry only PK000022 for svc 20392); add the Flying Gang sub-PK to lcc-coding-review so the recode validates. 3 Advisory: fix line 02 narration. | NA72312_Evidence/ (IKEA TE004431; Empire RL196475; ledger extract) | CN-23167 (journal-ready, Spero) | 8-Jun-2026
P2 | 73126 | Landscapers & Gardeners | 13198801.71 | 15381294.96 | >= $1M | Not started |  | 13198801.71 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P2 | 73212 | Major Contracts | 7765424.12 | 5318104.34 | >= $1M | Partial | 54242.75 | 7711181.37 | AMBER | RED | AMBER | AMBER | AMBER | A1 Strategy $15,100 (PO 708258) fails 73212 twice: four-element consultancy test met AND PO sits under the $20,000 floor; recode candidate to 73601 held (Tier 1 complete: 3 invoices + ABR x2 + ASIC, GST exact, hours recompute). Aust Care $630 invoice names PK000496, ledger charged PK000469 (PK recode candidate). GJ079210 -$66,183.82 one-sided Play Force move is the open dollar; ~$30,000 standing-order lines vendor-blind. ¦ 11-Jun: GJ079210 backup SIGHTED - balanced 6-line PK move PK000035 to PK0... | 1 Spero rulings: A1 $15,100 73212->73601 (73603 alt); Aust Care PK000469->PK000496 $630. 2 GJ079210 + GJ076924 backups CLOSED 11-Jun-2026 (sighted, balanced, direction verified). 3 Vendor invoices for s4090230 standing orders (~$30,000). 4 Contracts vs the $20k floor: LCC-09-2022, Aust Care SO, Play Force. 5 Trace IPWEA $343.20 part-payment. 6 Confirm Anita Moore home service (OrgRisk invoice now corroborates Acting Parks Manager). | NA73212_Evidence/ (8 files, hash-verified) | n/a (candidates held, no recode staged) | 10-Jun-2026
P2 | 73123 | Maintenance Services | 3900770.79 | 8330733.3 | >= $1M | Opened | 0 | 3900770.79 | n/a | n/a | n/a | n/a | OPENED | OPENED ONLY, no limb rated. Export sums $3,951,109.43 vs SE2 (8-Jun) $3,900,770.79: gap $50,338.64 unresolved (suspected export row duplication - 365 exact-duplicate rows $20,201.46, accrual legs appearing in triplicate - and/or 8-to-11-Jun P12 timing). Per session rule no conclusions until reconciled, so Reviewed-$ stays $0. Profile: AP $3,971,119.30 over 3,339 rows; GL net -$23,019.35 (self-reversing EOM accruals + 2 Pool Shop recodes out); top services 20392 $1,304,200 and 20481 $1,273,366 (6... | 1 Resolve the $50,338.64 export-vs-SE2 gap (re-pull or P12 diff) BEFORE any line work. 2 Read jointly with 73212 (GJ076924 redistribution touches both). 3 Plan line review by service: 20392 and 20481 first. | NA73123_Scope_Note.md; NA73123_Evidence/ (full + 2 section ledger extracts) | n/a (not worked) | 11-Jun-2026 (opened)
P2 | 73990 | Expensed capital services | 3051433.74 | 4000000 | >= $1M | Not started |  | 3051433.74 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 7C111 | Internal - Vehicle/Plant Hire | 1844939.64 | 2130960 | >= $1M | Not started |  | 1844939.64 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 7B115 | Internal - Garbage Charges | 871434.07 | 29417.39 | $100k-1M | Not started |  | 871434.07 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 73121 | Cleaning & Sanitary | 668784.41 | 1160178.75 | $100k-1M | Not started |  | 668784.41 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 7B112 | Internal - Water Base Charge | 363931.78 | 346422.15 | $100k-1M | Not started |  | 363931.78 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 7B113 | Internal - Water Usage Charge | 339375.43 | 276596.57 | $100k-1M | Not started |  | 339375.43 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 73124 | Security | 264132.36 | 5579.2 | $100k-1M | Not started |  | 264132.36 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 73211 | Minor Contracts (below $20,000) | 236077.27 | 894312.41 | $100k-1M | Fully reviewed | 236077.27 | 0 | AMBER | AMBER | AMBER | AMBER | AMBER | Reconciles to the 11-Jun SE2 to the cent: $236,378.27 register basis, 114 lines, 23 cost codes (this sheet carries the 8-Jun SE2 actual $236,077.27; the $301.00 difference is the P12 Lockwise line 2908883 posted 8-Jun-2026). Intake C00228240 applied 11-Jun: 43 documents sighted, $157,051.42 (66.4%) evidenced, every document exact on the x1.1 test, 18 ABN checksums PASS. Findings: F1 $5,635 GJ079190 duplicates GJ079210 onto PK000022 (Gihani 6-May-2026 instruction sighted: 510>PK000023, 511>PK000022); F2 ~$98,005 above-threshold candidates to 73212 (LCC31326 $25,848.08, Destination Trails $43,114, Chronicle $29,042.45); F3 training/chair items (PRINCE2 $2,440, PSIA $4,300, IPWEA $2,788, chair $370.05); F4 GJ078546 destinations unverified plus Provac $2,050 inbound query; F7 TE004838 cover slip vs posting mismatch; F5 and F6 CLOSED. Six new classification candidates (Firesight 73601, Chronicle 73566/survey, Tennyson 72222, SC10918 64411, Telstra telecoms, INCON materials). GSTE-28 Telstra cents-level pattern. | 1 Spero rulings on F1 (reversal and re-post destination), the F2/F3 candidate sets and the six new candidates (single sweep). 2 Sight the remaining gap documents ($79,326.85 incl 2906937 $10,200, 2908705 $17,000, TBM series $15,604.11, Ausecology $14,840). 3 Run the ABR sightings queue (18 suppliers; INCON and IPWEA done). 4 No recode dollar populates without the ruling. | 02_NA73211_Minor_Contracts/ (Verification Record; 43 evidence PDFs + manifest with GAP rows; Related/) | n/a (no recode staged; candidates held un-instructed) | 11-Jun-2026
P3 | 7B114 | Internal - Sewerage Charges | 204911.46 | 197323.14 | $100k-1M | Not started |  | 204911.46 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 7C112 | Internal - Miscellaneous Plant Hire | 163135.45 | 0 | $100k-1M | Not started |  | 163135.45 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 73312 | Electricity | 157505.76 | 174568.78 | $100k-1M | Not started |  | 157505.76 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P3 | 72231 | Landscape Supplies | 150347.57 | 99731.71 | $100k-1M | Not started |  | 150347.57 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 73544 | Training & Development | 69232.16 | 65134.88 | $10k-100k | Fully reviewed | 69232.16 | 0 | AMBER | AMBER | AMBER | AMBER | AMBER | Account reconciles. 21 references evidenced incl Whitehead $18,750, Fire Mgmt $10,500, Bendelta $8,966.28 (consultancy recode candidate to 73601), BAL $1,767 (73541 candidate; HLW dossier sighted, tax invoice outstanding), PSIA narration error. GST errors: Blue Dog $11.73 (GSTE-25), Barter $9.52 (GSTE-26), OIR $8.76 corrected (GSTE-27). 11-Jun: PK-split recode STAGED $2,131.46 (GJ079650 chargebacks $949.64 + ACCA split $1,181.82, 9 lines, nets $0.00, re-verified); Pryor/Hambly held; Preussner GJ... | 1 Upload NA73544_GENJNL_Recode.txt (in the live journal). 2 Spero rulings: Bendelta->73601 $8,966.28; BAL 73541-vs-73544 $1,767; Warnholtz concurrence; Pryor PK000044-vs-PK000003 $214.00; Hambly $294.42 (not in map); Preussner destination query. 3 Sight: HLW tax invoice, OIR source receipt, 7 journal backups ~$11,100. 4 Confirm Moore/Moir/Funk services (EOM report). 5 BAS: GSTE-25/26 reversals. ¦ 11-Jun: journal backups now 6 outstanding (~$10,600: IJ074222, GJ078710, GJ078895, GJ077155, GJ079267, GJ078296); OIR source receipt CLOSED. | NA73544_Evidence/ (36 files: session set hash-verified + back-charges set hashed this session) | CN-23167 (journal-ready, Spero 11-Jun-2026; NA73544 PK-split stream in the live journal) | 11-Jun-2026
P4 | 73422 | Fire Levy | 63803.78 | 60788.01 | $10k-100k | Not started |  | 63803.78 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 73535 | Tollway Charges | 46010.25 | 44775.05 | $10k-100k | Not started |  | 46010.25 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 73601 | Management Consultancies | 46003.66 | 45000 | $10k-100k | Fully reviewed | 46003.66 | 0 | GREEN | GREEN | GREEN | GREEN | GREEN | Full account parsed, 9 lines $46,003.66, reconciles to SE2 exact. Single engagement: Organisational Risk Consulting Pty Ltd, Parks Branch WHS Gap Analysis (Consultancy Agreement, T&M, consultant Andrea Paynter, PO 711200/712924). 1 of 9 invoices sighted: INV-251010(2) $2,132.63 via GJ078546, GST $213.26 exact, $2,345.89 incl = GL x 1.1 exact; consultancy four-element test met on the face; 73601 correct. Invoice addressee corroborates Anita Moore as Acting Parks Manager (bears on her home-service... EVIDENCE CLOSED 16-Jun: 8 Org Risk Consulting invoices sighted ($43,871.03 exact), 9 of 9, all A | 1 Obtain the 8 Org Risk invoices ($43,871.03). 2 Run ABR/ASIC dossier on ABN 27 651 588 662 when the set lands. 3 Check engagement period vs the 12-month contractor cap (runs 30-Jul-2025 onward on sighted docs). | NA73601_Evidence/ (INV-251010(2) + ledger extract); NA73601_Evidence_Manifest.csv (gap-listed) | n/a (no recode expected; coding correct on sighted line) | 11-Jun-2026
P4 | 7B111 | Internal - Rates & Charges | 34840.97 | 3663.8 | $10k-100k | Not started |  | 34840.97 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 72315 | Parks Assets | 27971.77 | 0 | $10k-100k | Not started |  | 27971.77 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 72112 | Chemical, fertiliser & paints | 27073.1 | 2624.88 | $10k-100k | Not started |  | 27073.1 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 72114 | Uniforms | 26236.42 | 49051.52 | $10k-100k | Partial | 1059.76 | 25176.66 | AMBER | GREEN | AMBER | N/A | AMBER | 3-Jun Reali PK split $1,059.76 confirmed subset (~4%). GJ SOURCE NOW SIGHTED (Document Reconstruction, doc 202603161072172000000001, ledger 26SLACT): a BALANCED multi-account recode batch (nets $0.00). Its 72114 block credits $10,650.27 from 1-20001-72114 narrated 'Institute of Public Works Engineering Au' (IPWEA) and DEBITS the same $10,650.27 across 16 service-level 72114 (Uniforms) PKs. CONCERN: if the $10,650.27 is a genuine IPWEA professional charge it should leave 72114 entirely (73542 Pro... | 1 Confirm whether the reconstruction batch is POSTED or PROPOSED; if posted, the IPWEA $10,650.27 is already spread across Uniforms service PKs. 2 Obtain the underlying IPWEA invoice to confirm nature (membership vs conference vs training) and set destination (73542/73541/73544); it should not sit in 72114. 3 Work the now-provided Reali set at full scope. 4 Confirm net-movement vs full-reversal format. Same batch also shows other apparent miscodes outside scope (e.g. Empire Office Furniture $4,300 in 73544 Training). ¦ 10-Jun: Reali Mar-2026 invoice sighted (GSTE-06 $0.01 note); officer split basis captured, not journalled | NA72114_Scope_Note.md; Document_Reconstruction (GJ source) sighted; C00223414 Reali set provided; 00_Uniform_Listing_72114.xlsx (full account, per-line) | CN-23167 (journal-ready, Spero) | 9-Jun-2026
P4 | 72113 | Safety Equipment & Medical Supplies | 25223.19 | 44586.46 | $10k-100k | Not started |  | 25223.19 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 7B122 | Internal - Tip Fees | 23267.12 | 10492.41 | $10k-100k | Not started |  | 23267.12 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 73122 | Garbage Collection | 21876.6 | 1152061.69 | $10k-100k | Not started |  | 21876.6 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 73609 | Other Consultancies | 21730 | 0 | $10k-100k | Not started |  | 21730 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 73128 | Other services | 17155.73 | 5469.81 | $10k-100k | Partial | 1854.7 | 15301.03 | GREEN | RED | GREEN | GREEN | AMBER | $1,854.70 of $1,854.70 (100%) of the milk spend miscoded to 73128 last-resort services; goods purchase belongs in 73512 Entertainment & Hospitality Non-FBT (recode instructed by Spero 10-Jun-2026). All 50 unique invoices and the bond refund documents sighted; account reconciles to the ledger with no residual. 16 GST errors confirmed, $61.11 ITC over-claimed Jun-2025 to mid-Sep-2025 (corrected at source from INV-399504), recorded GSTE-07 to GSTE-22; bond refund net-nil GST timing note $272.73 rec... | 1 Upload NA73128_GENJNL_Recode.txt (122 lines, 61 pairs, nets $0.00, direction verified). 2 Process the $61.11 BAS adjustment (GSTE-07 to GSTE-22); no GENJNL movement. 3 Package the 56 per-line evidence PDFs into NA73128_Evidence/ (sighted 10-Jun-2026, SHA-256 fingerprints held in NA73128_Workstream_Manifest_10-Jun-2026.csv; only the compressed second-intake binder is carried this bundle). | NA73128_Evidence/ (second-intake binder C00216123; ledger extract; ABR record); NA73128_Evidence_Manifest.csv (59 rows, no GAP) | CN-23167 (journal-ready, Spero 10-Jun-2026) | 10-Jun-2026
P4 | 73412 | Refund of Operational Contributions | 15477.09 | 0 | $10k-100k | Not started |  | 15477.09 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 7B411 | Internal - IT Equipment & Application | 13130 | 1640.95 | $10k-100k | Not started |  | 13130 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 7B211 | Internal - Property-based Professional S | 11000 | 1934.81 | $10k-100k | Not started |  | 11000 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P4 | 7BZ11 | Internal - Community Service Obligations | 10929.72 | 4088.78 | $10k-100k | Not started |  | 10929.72 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 7B123 | Internal - Other fees & Charges | 9542.69 | 945.91 | $1k-10k | Not started |  | 9542.69 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73563 | Printing & Stationery | 9495.37 | 7322.24 | $1k-10k | Fully reviewed | 9495.37 | 0 | GREEN | RED | GREEN | GREEN | AMBER | $6,354.47 of $9,495.37 (66.9%) miscoded out of 73563 (WINC catch-all + Officeworks TE005250); recode journal-ready. Evidence re-verified 10-Jun-2026: all eleven WINC tax-invoice summaries sighted and reconciled per cost centre to the cent (GL ex-GST base equals invoice ex-GST every month); GST-free refreshment content (34 lines $1,195.79) correctly booked off invoice GST, no phantom ITC; stores lines 094908/096380 closed under the Marsden convention (envelope item 207144, code collision document... | 1 Upload the 73563 recode (in the live journal). 2 50/50-batch data check on the 73512 movements (Reason B). 3 Sight the TE005154 backup ($136.80) - the last evidence item - or Spero waiver. | NA73563_Evidence/ (11 WINC invoices incl 9 newly sighted P1-P10, Officeworks 628185694, audit, recon, ledger) | CN-23167 (journal-ready, Spero) | 9-Jun-2026
P5 | 74189 | Fuel Levy Surcharge | 9075.51 | 0 | $1k-10k | Not started |  | 9075.51 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73111 | Property-based Professional Services | 8000 | 10443.15 | $1k-10k | Not started |  | 8000 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 7B532 | Internal - Spoils | 6032 | 5469.81 | $1k-10k | Partial | 2944 | 3088 | GREEN | GREEN | AMBER |  | AMBER | $2,944.00 over 3 internal journal lines on 1-20451-7B532 PK000403 (Cemeteries spoils). $16 per unit rate validated (IJ073064 $480 = 30 units x $16 exact; 28-Jul-2025 sheet 77 units x $16 = $1,232 exact). IJ073064 cleared GREEN; one IJ072723 $1,232 posting evidenced; the identical second posting is a probable duplicate over-charge, held AMBER not RED because the corrupted week-ending narration ("W/E 01-Jan-1900 Week 0") keeps a weekly charge basis in play. Tax limb n/a (internal charges, no GST uplift). Untested remainder sits outside the 3-line export. | 1 Obtain the Bega Road sheets for the week 28-Jul-2025 to 3-Aug-2025 to resolve the probable $1,232 duplicate. 2 Raise the quarry-returns week-ending field corruption with the system owner (affects all 7B532 narrations). | 04_NA7B532_Internal_Spoils/ (Verification Record; evidence manifest; two Bega Road sheets) | n/a (no recode staged) | 11-Jun-2026
P5 | 73545 | Study Assistance Reimbursement | 5840.65 | 8521.61 | $1k-10k | Not started |  | 5840.65 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73512 | Entertainment & Hospitality Non-FBT | 5512.55 | 4314.07 | $1k-10k | Fully reviewed | 5512.55 | 0 | AMBER | AMBER | AMBER | AMBER | AMBER | Account reconciles to the cent. 5 of 6 volunteer reimbursements fully evidenced (Hoffmann x3, Preussner x2, GST exact, identity matched); Warnholtz AP003847 asymmetry resolved (GSTE-24). Open: Quote 5468 $1,656.50 vendor unknown (largest unevidenced line), Salisnew ~$234, ~100 FBT-batch micro-lines. | 1 Sight 12052026 Preussner receipt $27.79. 2 Identify Quote 5468 vendor + invoice. 3 Salisnew receipts x6. 4 Micro-line population: pcard docs OR Spero waiver. 5 Confirm TE005497/AP003877 $97.00+$7.90 split. | NA73512_Evidence/ (5 receipts + 2 identity docs, hash-verified; identity docs carry full bank details, restrict to folder) | n/a (no recode staged) | 10-Jun-2026
P5 | 73215 | Major Contracts – Partnership | 4739 | 0 | $1k-10k | Fully reviewed | 4739 | 0 | GREEN | RED | GREEN | GREEN | AMBER | $4,739.00 of $4,739.00 (100%) miscoded into 73215, a RESTRICTED Alliance account (CEO approval required); none of the spend is Alliance partnership work. All 3 invoices SIGHTED 11-Jun-2026 and reconcile to the cent: TEC 3043 $2,340.00 (mow/brushcut Bromley St Cornubia, PAR/336K/2024), Austspray 155797 $900.00 (fenceline clean-up Yarrabilba), Austspray 157909 $1,499.00 (Frankland Ave infill planting). All on PK000366 General Landscape Improvement Fund, matching invoice PK refs. ABNs checksum PASS... | 1 Spero ruling on the 73215 to 73126 recode $4,739.00 (candidate held, un-instructed; restriction handling on the source leg to confirm). 2 Advisory: vendor masked by STANDING ORDER 24/25 narrations; invoices supply Tier 1. | NA73215_Evidence/ (3 invoices + ledger extract, SHA-256 in NA73215_Evidence_Manifest.csv) | n/a (candidate held, no recode staged) | 11-Jun-2026
P5 | 73313 | Telecommunication Services | 4580.55 | 10101.86 | $1k-10k | Not started |  | 4580.55 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73511 | Entertainment & Hospitality FBT | 4267.49 | 3608.47 | $1k-10k | Fully reviewed | 4267.49 | 0 | AMBER | AMBER | AMBER | AMBER | AMBER | Full account $5,384.57 ex-GST net of Finance FBT batch pairs (58 lines net $0.00, set aside; 2 AP003801 re-posts live). Annotated export = claims, not Tier 1; candidates quantified, NOT journalled: $762.33 to 73512 (amenity $334.71, non-employee $301.71, training catering $125.91), Warnholtz $744.30 to 73544, $23.56 utensils to 72111; Daily Blooms $88.14 customer-gift query. STAY-FBT $3,664.79 incl unsighted INV-9747 $2,445.45. One $4.18 doesnt-reconcile RED; $97.27 unannotated. ¦ 11-Jun: INV-97... | 1 Spero ruling on the 73512/73544/72111 candidate set + Daily Blooms class 2 Sight INV-9747 ($2,445.45, vendor unidentified) and Warnholtz 001 3 Identify Hoffmann/Bahry/Warnholtz/Salisnew (not in employee map); confirm Mann/Rosmarin sections 4 Receipts for the PCard food population (GST-free mix) 5 Classify 4 unannotated lines ¦ 11-Jun: INV-9747 sighted and vendor identified (item 2 partially closed; Warnholtz 001 remains). New: trace the $700 room hire payment and $200 bond return on the Greenbank engagement. | NA73511_Evidence/ (annotated ledger extract; no receipts sighted) | n/a (no recode staged) | 10-Jun-2026
P5 | 73552 | Other Advertising | 4140.63 | 1044.32 | $1k-10k | Not started |  | 4140.63 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72222 | Signs | 4047.1 | 0 | $1k-10k | Not started |  | 4047.1 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 7B213 | Internal - Medical Services | 3996.8 | 0 | $1k-10k | Partial | 3996.8 | 0 | AMBER | GREEN | AMBER |  | AMBER | Whole-branch immunisation miscoded to NatAreas PK000432 via Internal_Medical.XLSM row 23 (svc 20318). Coding/PK review complete; svc-PK split staged $3,799.50, 17 pairs, nets $0.00 (register export basis $4,861.70; SE2 $3,996.80). Stays on PK000432 $541.30; off-branch $520.90 incl $146.30 duplicate to Finance. Evidence all unsighted (GAP); SE2 not yet tied; internal account, no GST event (L4 n/a). AMBER. | Not started. Obtain TechOne ledger export to open.
P5 | 73140 | Pre-Employment Background Checks | 3703.03 | 0 | $1k-10k | Partial | 3703.03 | 0 | GREEN | GREEN | AMBER | AMBER | AMBER | Carried from 3-Jun pass. 21 lines, single vendor (CV Check), narration consistent, NA matches chart definition; coding correct. $58.02 GJ EOY reversal normal. Tier-3 sighting only: AP invoices not sighted, so evidence and tax limbs remain open. | 1 Sight a sample of CV Check AP invoices to confirm evidence and tax limbs. 2 On sighting, clear to GREEN (no recode expected). | 3-Jun review queue finding (no deliverable bundle this pass) | n/a (no recode) | 9-Jun-2026
P5 | 7B214 | Internal - Maintenance Services | 3682.5 | 8811.98 | $1k-10k | Fully reviewed | 3682.5 | 0 | AMBER | AMBER | AMBER |  | AMBER | Full 3-line internal population reviewed; the register carries $7,570.50 including the P12 IJ074845 $3,888.00 posted 10-Jun-2026 after the 8-Jun SE2 cut (this sheet's accum actual $3,682.50; basis difference $3,888.00). IJ074028 Marsden rodent control $82.50 cleared on Tier 1 (CSL invoice sheet + Durant email 5-Feb-2026; oncharge passed through at invoice price, exact). Remaining $7,488.00 unsighted: IJ073869 Tully Memorial Park signage modification $3,600.00 (Transport Operations oncharge; reads closer to works than maintenance services) and IJ074845 DA/4574 backflow annual renewal notices $3,888.00 (svc 20361 attribution to confirm). Tax limb n/a (internal charges). | 1 Obtain the Transport Operations oncharge backup for IJ073869 ($3,600.00). 2 Obtain DA/4574 for IJ074845 ($3,888.00) and confirm the svc 20361 attribution. | 05_NA7B214_Internal_Maintenance/ (Verification Record; evidence manifest; CSL sheet + Durant email) | n/a (no recode staged) | 11-Jun-2026
P5 | 73127 | Electrical Maintenance | 2068.21 | 72962.51 | $1k-10k | Not started |  | 2068.21 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73311 | Gas | 1661.01 | 568.34 | $1k-10k | Not started |  | 1661.01 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 7B121 | Internal - Trade Waste Charges | 1643.76 | 1627.07 | $1k-10k | Not started |  | 1643.76 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73115 | Medical Services | 1576.65 | 1892.98 | $1k-10k | Not started |  | 1576.65 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72313 | Furniture & Fittings | 1313.28 | 2231.71 | $1k-10k | Not started |  | 1313.28 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73543 | Reference Materials and Subscriptions | 1267.18 | 0 | $1k-10k | Not started |  | 1267.18 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73141 | Drug & Alcohol Testing | 1246 | 0 | $1k-10k | Not started |  | 1246 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 74114 | Water Truck | 1137.45 | 0 | $1k-10k | Not started |  | 1137.45 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73125 | Workplace Health & Safety | 1098.04 | 0 | $1k-10k | Not started |  | 1098.04 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73533 | Interstate Travel and Accommodation | 1021.7 | 1031.54 | $1k-10k | Fully reviewed | 1021.7 | 0 | GREEN | GREEN | GREEN | GREEN | GREEN | $1,015.15 of $1,021.70 confirmed interstate. TE005080 = ONE PCard ref over TWO lines: hotel $288.18 (L07) + 7-Eleven $6.55 (L02). BOTH NOW RESOLVED (9-Jun). 7-Eleven receipt SIGHTED: 7-Eleven 1130 Melb Queen St, ABN 86 960 363 023 checksum PASS, TAX INVOICE, 1x ham pesto sandwich $7.20 incl, GST $0.65, ex $6.55; cover slip "Dinner/Breakfast", Quinn. A meal during travel never sits in 73531-73534, so the $6.55 RECODES to 73512 Non-FBT (Reason B refreshment; sole traveller, no alcohol/social = not... | None gating. Advisory only: obtain the ibis Melbourne (Accor) tax invoice if convenient to retire the $28.82 ITC exposure noted in the finding. Recode pair ($6.55 73533->73512) ready in batch. | NA73533_Evidence/ (7-Eleven receipt L02 + Booking.com ibis hotel L07 both filed; ledger extract) | CN-23167 ($6.55 73533->73512 posted) | 9-Jun-2026
P5 | 73542 | Professional Membership | 938.18 | 1168.81 | < $1k | Not started |  | 938.18 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 74184 | Oils & Grease | 908.99 | 0 | < $1k | Not started |  | 908.99 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72411 | Bulk Water | 816.8 | 0 | < $1k | Not started |  | 816.8 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73513 | Employee Reward and Recognition | 704.79 | 0 | < $1k | Not started |  | 704.79 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73541 | Conferences & Seminar Fees | 642.14 | 8375.87 | < $1k | Fully reviewed | 642.14 | 0 | GREEN | GREEN | AMBER | AMBER | AMBER | 6 lines net $642.14 (svc 20641 PCard plus closed recode and reversal pairs). TE004218 $6.05 Gold Coast parking miscode CLOSED: recoded to 73531 via GJ078933 (14-Apr-2026), pair nets $0.00, direction correct, closing the restored 3-Jun travel flag. GJ075544 +/-$44.89 EOY 2024/25 AP reversal pair nets out (Canungra accommodation content is an FY25 advisory; accommodation never belongs on 73541). Open: TE004922 Trailbuilders conference registration $626.48 unsighted (correct 73541 content on its face) plus a $15.66 international transaction fee, strictly a financing cost, immaterial, advisory only. | 1 Sight the Trailbuilders registration backup for TE004922 ($642.14 combined) on the PCard reconciliation. | 06_NA73541_Conferences/NA73541_Notes_and_Kinatico_Intake.md (none sighted) | n/a (TE004218 recode already in-ledger via GJ078933) | 11-Jun-2026
P5 | 73137 | Excess and Damages Payments-Other | 487.05 | 0 | < $1k | Not started |  | 487.05 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72211 | Bitumen & Asphalt Products | 426.79 | 0 | < $1k | Not started |  | 426.79 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 7B611 | Internal - Property Leases & Rentals | 422.1 | 0 | < $1k | Not started |  | 422.1 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 7B521 | Internal - Crushed Gravel | 384 | 0 | < $1k | Not started |  | 384 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 74183 | Fuel | 369.81 | 0 | < $1k | Not started |  | 369.81 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 74187 | Rego, Licences & Third Party | 337.58 | 0 | < $1k | Not started |  | 337.58 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72214 | Construction Materials | 262.38 | 0 | < $1k | Not started |  | 262.38 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73531 | Local Travel (SEQ) Cabcharge/Parking | 221.41 | 2631.47 | < $1k | Not started |  | 221.41 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 74161 | Other Plant Hire | 207.89 | 0 | < $1k | Not started |  | 207.89 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72311 | Other Plant & Equipment | 159.42 | 0 | < $1k | Not started |  | 159.42 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73433 | Other Fees & Charges | 139.25 | 0 | < $1k | Fully reviewed | 139.25 | 0 | AMBER | RED | AMBER | AMBER | AMBER | $34.55 of $139.25 (24.8%) miscoded: QUT visitor parking belongs in 73531 Local Travel SEQ (GJ078933 precedent). Blue card $104.70 correctly recoded in from 73544; original TE004496 receipt unsighted. ¦ 11-Jun: TE004496 receipt SIGHTED - Blue Card Services 56213618922, Preussner renewal $104.70, Div 81 GST exempt, booked gross with no ITC, Dyba PCard, slip coded PK000075-73544. Evidence gap CLOSED. | 1 Upload NA73433_GENJNL_Recode.txt (in the live journal; 73433->73531 $34.55, PK000087, nets $0.00, direction verified). 2 TE004496 blue card receipt SIGHTED 11-Jun-2026 (gap closed). 3 Confirm TE005281 cardholder. | NA73433_Evidence/ (QUT receipt TE005281, hash-verified) | CN-23167 (journal-ready, Spero 10-Jun-2026; NA73433 stream in the live journal) | 10-Jun-2026
P5 | 72118 | Fuel Card - Pending Account | 108.08 | 0 | < $1k | Not started |  | 108.08 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73561 | Other Administration Costs | 88.14 | 0 | < $1k | Not started |  | 88.14 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72212 | Concrete | 84.06 | 0 | < $1k | Not started |  | 84.06 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73553 | Promotional Items | 14.56 | 0 | < $1k | Not started |  | 14.56 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73421 | Rates & Charges paid | 0.36 | 0 | < $1k | Not started |  | 0.36 | [6 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72221 | Roads & Parks Furniture | 0 | 37464.81 | zero / credit | Not started | [8 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 72248 | Crusher Dust | 0 | 2231.91 | zero / credit | Not started | [8 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73532 | Intrastate Travel and Accommodation | 0 | 0 | zero / credit | Not started | [8 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 74141 | Trucks to 8 tonnes G.V.M. | 0 | 22407.93 | zero / credit | Not started | [8 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 7B219 | Internal - Other Services | 0 | 3281.88 | zero / credit | Not started | [8 empty] | Not started. Obtain TechOne ledger export to open.
P5 | 73213 | Contractor Entitlements | -11680 | 0 | $10k-100k | Not started |  | -11680 | [6 empty] | Not started. Obtain TechOne ledger export to open.
SUPPLEMENTARY - outside the 87-account expense scope (revenue; carried on the register, excluded from the KPI ranges above)
SUPP | 62121/62125 | Cemetery Revenue (Garside query) |  |  | revenue | Fully reviewed | 3711.73 | 0 | AMBER | GREEN | AMBER | AMBER | AMBER | Garside query (29-Aug-2025) already actioned in-ledger: GJ076150 (1-Sep-2025) reversed both PK000400 pre-purchase lines ($1,552.73 + $2,159.00 = $3,711.73) off 1-20446-62125. Five sighted documents reconcile to the cent; the King paper trail is closed (498178 charged GST in error, CN 140775 credited, 501999 reissued GST-correct) and CN 140799 Timmins plot-fee error cleared. GST treatment consistent (plots GST-free, interments taxable); nil GST Errors Register entries. $ incl GST is per-line, not a blanket 1.1 uplift. | 1 Pull the GJ076150 destination legs and confirm the receiving PK disburses to svc 20451. 2 Sight burial-fee invoices 505970 ($2,812.73 SUSKI) and 506368 ($204.55 HALA'UFIA). 3 Advisory: the ashes interment component arguably sits closer to 62121 than 62125. 4 Scope call: the 56-line event-fee export (-$61,364.17) awaits a ruling. | 03_Cemetery_Revenue_62121_62125/ (Verification Record; 5 evidence docs + Garside email) | n/a (no recode staged; GJ076150 already in-ledger) | 11-Jun-2026

## Open Items
CN-23167 Open Items Register - everything still open, by account
Mirrors 00_Outstanding_Evidence_and_Actions.md as at 11-Jun-2026 (fourth pass) ¦ Documents to sight, Spero decisions, internal work ¦ Hard gates: NONE
# | Type | Account | Item | Status / note
1 | Document | 73511 | Warnholtz invoice 001 ($744.30, narrated Training) | GAP; payee not in employee map
2 | Document | 73511 | Receipts for the PCard/reimbursement net population | GAP; per-line GST-free food check pending
3 | Document | 73511 | Greenbank engagement residuals: the $700.00 room hire payment trace and the $200.00 bond return | GAP; non-blocking on the INV-9747 line
4 | Document | 73533 | ibis Melbourne (Accor) tax invoice for the $288.18 accommodation | Advisory; GST waived by Spero, ITC exposure noted
5 | Document | 73140 | Sample of CV Check AP invoices | GAP; numbers unknown
6 | Document | 73140 | FY26 73140 ledger extract, to apply the five held Kinatico invoices (P00075671, P00081314, P00082255, P00083290, P00086890; ABN 25 111 728 842, PO 801790) | NARROWED 11-Jun-2026: invoices in hand in 07_Intake_Held_Kinatico/ (Kinatico is the CVCheck parent); held unapplied per the evidence rule, zero AP document hits in the 11-Jun exports
7 | Document | 73564 | SR backups: SR219175 (Robertson), SR-0315517 (Fry) | GAP; SR235810 (Dresman) CLOSED 10-Jun; lines journal-ready on directive
8 | Document | 73564 | Other no-attachment SR backups and five external invoices (2412569490, INAU004378, GJ076194, GJ075813, TE005499) | GAP; six off-home lines still open
9 | Document | 72111 / 72114 | Full ledger remainders | GAP; large untested balances
10 | Document | 73128 | Per-line evidence split set (56 PDFs; all 50 TCB invoices + bond support) | Packaging GAP only; all sighted 10-Jun-2026, SHA-256 fingerprints in NA73128_Workstream_Manifest_10-Jun-2026.csv
11 | Document | n/a (unplaced) | BCC King George Square parking receipt 89991, 4-Jun-2025, $42.15 net + $4.21 GST (card ...1627 Anita Moore) | Identified-unplaced; FY25 document, no in-scope FY26 match; likely FY25 73531; archived _Sources_10-Jun-2026/ pending instruction
12 | Document | n/a (unplaced) | Six IPWEA documents (R58890, 40310, 40309, two QNT Stripe receipts x3 copies) | Identified-unplaced; attendees not in Parks; archived _Sources_10-Jun-2026/ pending instruction
13 | Document | 73512 | Preussner 12052026 receipt, $27.79 (last reimbursement gap) | GAP
14 | Document | 73512 | Quote 5468 vendor tax invoice, $1,656.50 (vendor unknown; largest unevidenced line) | GAP
15 | Document | 73512 | Salisnew direct claim receipts ~$234 (six refs) | GAP
16 | Document | 73512 | Micro-line population PCard docs (refs 1179861-1211218, TE004278-TE005497, ~100 lines) | GAP or Spero waiver
17 | Document | 73544 | Healthy Land & Water tax invoice for the BAL workshop $1,767 | NARROWED 10-Jun-2026: ABR + ASIC dossier sighted; the compliant tax invoice itself remains the gap, tax limb AMBER
18 | Document | 73544 | Internal journal backups x6 (~$10,600: IJ074222, GJ078710, GJ078895, GJ077155, GJ079267, GJ078296) | GAP; GJ079650 CLOSED 10-Jun; GJ076597 CLOSED 11-Jun-2026
19 | Document | 73544 | IPWEA $343.20 part-payment posting trace (39657) | GAP
20 | Document | 73544 | Preussner GJ078933 -$3,044.65 destination query | REOPENED 11-Jun-2026: 73545 versus 7B411 on the $931.20 leg; one ruling closes it
21 | Document | 73212 | Vendor invoices for s4090230 standing-order lines (~$30,000) | GAP; GJ076924 backup CLOSED 11-Jun-2026 (PK000415/PK000429 not in maps - documented 11-Jun in lcc-coding-review as unmapped journal PKs pending confirmation)
22 | Document | 73212 | Contract documents for the $20,000 floor test: LCC-09-2022 (Harpley), Aust Care standing order, Play Force engagement | GAP; the intake Play Force AP ledger ($97,347.39, INV-7594 to INV-7733) feeds the Play Force floor test
23 | Document | 73601 | Eight Org Risk Consulting invoices (INV-250714, INV-250811 to 250813, INV-250910 to 250913), $43,871.03 | GAP; INV-251010(2) $2,132.63 sighted and exact
24 | Document | 73123 | Export-vs-SE2 reconciliation, gap $50,338.64 (export $3,951,109.43 vs SE2 $3,900,770.79) | GAP; suspected export row duplication and/or P12 timing; BLOCKS all 73123 line work
25 | Document | 73211 | Remaining evidence gaps after intake C00228240: 2906937 ($10,200), 2908705 ($17,000), TBM 00097461/97583/97626/97780 ($15,604.11), Ausecology INV-4029/4030 ($14,840 via GJ078960), Provac INV-00037183 ($2,050), Telstra Dec-25 ($727.95), T2 3222869/3223786 ($1,820), 698933AU/713170AU ($2,433.44), EWN INV-14768, 9016 ($1,710), 00735 ($200), 34828 ($546.68), INV-38877 ($2,250), 00059013 + 00031055/79/85/86 + 00060617/47 series ($4,106.20) | NARROWED 11-Jun-2026: 43 documents SIGHTED, $157,051.42 of $236,378.27 (66.4%) evidenced, all exact; gap rows restated in NA73211_Evidence_Manifest.csv
26 | Document | 73211 | IPWEA $343.20 part-payment posting trace | NARROWED 11-Jun-2026: invoice 39657 shows Payment Received $343.20 ($312.00 ex + $31.20 GST); the posting location remains the trace
27 | Document | ALL NEW SUPPLIERS | ABR sightings queue: Destination Trails, Firesight, Reactive Generators, Chronicle Rip, Play Force, RST, CAASie, Tennyson, T2, Lockwise, IAS, PSIA, DDLS, EWN, Worssell, Empire, Telstra, Message4U | GAP; checksums all PASS; INCON and IPWEA ABR already sighted
28 | Document | 7B532 | Bega Road sheets for the week 28-Jul-2025 to 3-Aug-2025 | GAP; resolves the probable $1,232 IJ072723 duplicate
29 | Document | 7B214 | Transport Operations oncharge backup for IJ073869 ($3,600); DA/4574 for IJ074845 ($3,888) | GAP; $7,488 of $7,570.50 unsighted
30 | Document | 62121/62125 | GJ076150 destination legs (confirm receiving PK disburses to svc 20451); invoices 505970 ($2,812.73 SUSKI) and 506368 ($204.55 HALA'UFIA) | GAP; the destination confirmation is the residue of the Garside query
31 | Document | 73541 | Trailbuilders registration backup for TE004922 ($626.48 + $15.66 fee) | GAP; PCard reconciliation
32 | Decision | 73511 | Ruling on the candidate set: $762.33 to 73512 (amenity $334.71, non-employee $301.71, training catering $125.91), $744.30 Warnholtz to 73544, $23.56 utensils to 72111; Daily Blooms $88.14 customer-gift class | Held
33 | Decision | 72312 | 72312 to 72313 full-reversal - journal-ready (PK000493 Flying Gang sub-PK ADDED to lcc-coding-review 11-Jun-2026; pk_validator now passes) | Journal-ready
34 | Decision | 73564 | 73564 to 73566 software recode and the Body2 move-or-stay; the nine off-home PK lines (three confirmed and staged, six open) | Held / staged
35 | Decision | 73563 | WINC systemic recode out of 73563; TE005250 riser destination (72313); 73512 moves are Reason B (50/50 batch data check) | Journal-ready
36 | Decision | 72111 | PPE to 72113; STIHL to 72315; Posca to 73563; scrap income to 64411; desk-riser 72313 advisory. Tennyson 72222 CLOSED 10-Jun (Doc46 J22) | Journal-ready
37 | Decision | 72114 | Extending the Reali PK split to Mar-2026 (Namoa = Cemeteries PK000439, cross-section); net-movement vs full-reversal format; stores-issue footwear/respiratory-PPE class candidates (single ruling) | Held
38 | Decision | 73215 | Full account to 73126 Landscapers & Gardeners, $4,739.00, full-reversal, 3 pairs, nets $0.00 | Candidate HELD un-instructed (Tier 1 complete on 100% of dollars; source leg trips the 73215 Alliance restriction flag by design)
39 | Decision | 73128 | Full milk spend to 73512 - instructed by Spero 10-Jun-2026, journal-ready (122 lines, 61 pairs, nets $0.00, direction verified). Remaining: $61.11 BAS adjustment (GSTE-07 to 22) and per-line evidence packaging | Instructed
40 | Decision | 73433 | QUT parking 73433 to 73531 $34.55 - instructed 10-Jun-2026, in the live journal | Instructed
41 | Decision | 73544 | PK-split recode INSTRUCTED 11-Jun-2026 and staged ($2,131.46: GJ079650 chargebacks $949.64 + ACCA split $1,181.82, 9 lines, nets $0.00, re-verified) | Instructed
42 | Decision | 73544 | Still held: Bendelta $8,966.28 to 73601; BAL workshop $1,767 (73541 vs 73544, tied to the HLW invoice); Warnholtz $744.30; Barter blue card 73433 candidate; Pryor $214.00; Hambly $294.42; Preussner destination query | Held
43 | Decision | 73212 | A1 Strategy $15,100 to 73601 (73603 alternative) - Tier 1 complete; Aust Care PK $630 PK000469 to PK000496 | Candidates held
44 | Decision | 73512 | Micro-line evidence waiver (~100 FBT-batch transfer lines: PCard docs or waiver) | Held
45 | Decision | BAS / GST | GSTE-25 ($11.73 Blue Dog) and GSTE-26 ($9.52 Barter) ITC reversals - no GENJNL movement | Spero instruction pending
46 | Decision | 73211 | F1 GJ079190 ruling, ENRICHED 11-Jun: Gihani 6-May-2026 email directs 510>PK000023, 511>PK000022; both journals posted to PK000022. Ruling covers (a) full reversal and (b) whether the 510 batch re-posts to PK000023. GJ079210 stands; INV-5888 quantum invoice-confirmed | Held
47 | Decision | 73211 | F3 training and chair recodes - source evidence COMPLETE (PSIA, IPWEA, DDLS, Empire all sighted): PRINCE2 $2,440 to 73544; PSIA $4,300 + IPWEA $2,788 to 73544; chair $370.05 to 72313 | Destination ruling only
48 | Decision | 73211 | New candidates from intake C00228240 (single ruling sweep): Firesight $12,800 to 73601; Chronicle INV-0868 $5,812.45 to 73566; Chronicle mapping/imagery $23,230 survey-services class; Tennyson 27168 $1,058 to 72222; SC10918 -$154 to 64411 + cemeteries attribution; TE004838 $242.40 (F7 mismatch); Telstra series $9,237.48 telecoms class; INCON $25,848.08 materials-not-contracts | Held
49 | Decision | 73211 | F2 73211 to 73212 recodes ~$98,005 (LCC31326, Destination Trails series, Chronicle series) - all three series invoice-evidenced in full; treatment ruling pending; total contract value confirmation from contract files or standing orders | Held; no recode dollar populates without the ruling
50 | Decision | Scope | Unreviewed queue (parsed and totalled only): 72112 $27,073.10, 72113 $25,244.22, 7B111 $34,840.97, 7B114 $204,911.46, 7B213 $3,996.80, 7B411 $13,130.00, 7BZ11 $10,929.72, 72311 $159.42; plus the 62121 event-fee export (56 lines, -$61,364.17) | Confirm whether each joins the review
51 | Internal | Travel | Restored 3-Jun travel flags: Cabcharge Jan-2026 statement $787.74 per-traveller split (mixed 73531/73533). TE004218 CLOSED 11-Jun (GJ078933 verified) | Open (Cabcharge only)
52 | Internal | 72114 | Work the Reali set at full scope (Mar-2026 officer detail in hand; GJ079517 $45.29 cross-reference); review the 72111 and 72114 remainders | Open
53 | Internal | 73511 / 73512 | Identify Hoffmann, Bahry, Warnholtz and Salisnew (payees not in employee map); confirm Mann and Rosmarin sections; classify four unannotated 73511 lines ($97.27) | Open
54 | Internal | 73544 | Confirm Burke's Play Safety recode basis: home service resolved 10-Jun as 20362 / PK000435; apply when the recode is instructed | Open
55 | Internal | 72114 | Item-level tie-out of the GJ078546 redistribution to the five Reali invoices' per-officer detail (dedicated pass) | Open
56 | Internal | Scripts | build_listing.py does not rebuild the 73511 tab nor the five workstream tabs added 11-Jun-2026 (73211, 73541, 7B532, 7B214, 62121/62125 - built directly); build_master.py LINE_NAS extended 11-Jun for the four expense tabs | Queued
57 | Internal | People | Service confirmations (one EOM People and Positions pass): Anita Moore home service; TE005281 cardholder (QUT); Jennifer Moir; Leighton Funk | Open
58 | Internal | Scripts | build_listing.py and build_master.py do not yet cover the four merged accounts (73433, 73512, 73544, 73212) - TechOne exports not packaged; obtain exports, build tabs | Queued
59 | Internal | 73211 | SC10918 plaque credit attribution (-$154 on Depots PK000001; plaques are svc 20451) - original purchase line not in the 73211 listing; trail starts with AP | Open
60 | Internal | 7B532 | Quarry returns week-ending field corruption ("W/E 01-Jan-1900 Week 0") on all 7B532 narrations - raise with the system owner | Open
61 | Internal | Journals | GJ078546 / GJ079190 / GJ079210 narration quality (narrations describe neither leg) - note for the journal preparer | Open
62 | Register decision | Scope | Untested remainders: 72111 ($63,621.56) and 72114 ($25,176.66); 73564 untested remainder closed | Open
63 | Register decision | Sequence | Priority sequence: finish in-flight then materiality. P2 accounts 73126, 73212, 73123, 73990 | Open